## Slide 1: Increasing Utilization of Well Child Exams
Region 15 RHP Meeting
El Paso First Healthplan, 1145 Westmoreland Drive
Maria Theresa M. Villanos, MD
July 29, 2014
1:00pm

## Slide 2: Introduction
Completion of nationally recommended preventive pediatric health care (Periodicity) examinations in our population is challenging at all age ranges, and particularly after the 12 month visit.
A number of reasons may contribute to this
  Parental perceptions that “everything is all right”
  Transportation challenges
  The need to take off work and remove the child from school or day care
  Parental perceptions that the health maintenance examinations of older children are not important and not worth the time

## Slide 3: Introduction
The populations we most commonly serve, Hispanics with low household educational and higher levels of poverty, at are particular risk of not receiving health maintenance exams
Eighty-nine percent of the patients we treat in our after-hours acute care walk in clinic are uninsured, or have Medicaid or CHIP

## Slide 4: Description of the Project
Utilize a “just in time” delivery model to offer periodic health exams visit to all eligible children in the family of an index patient who presents to the walk-in clinic.
We do not intend to disrupt the traditional provider – patient relationship where one exists (and the parent is regularly accessing preventative care.)

## Slide 5: Description of the Project
Rather we are identifying children who have fallen off the recommended pathway, are not receiving services they are eligible for, and use the acute care visit as opportunity to both provide the screening examination and try to reestablish the patient with a Primary Care Provider for subsequent exams.
Re-establishing such a relationship may result in the child receiving future recommended periodicity exams and also reduced use of acute care services in the future.

## Slide 6: Description of the Project
Goal: To increase the number of children who receive appropriate health periodicity exams as defined by the American Academy of Pediatrics Bright Futures Recommendations and are current in their immunization status.
Expansion of pediatric primary care by providing health periodicity exams in conjunction with a visit to an acute care walk in clinic to eligible patients and their siblings

## Slide 7: Description of the Project
Departments Involved: PLFSOM Department of Pediatrics, Ambulatory Division

## Slide 8: Description of the Project
DY3 Milestones
Milestone: Increase access to primary care capacity.
  Metric: Documentation of increased number of unique patients.
  Goal: We will increase the number of unique patients who receive a Health Maintenance Exam in the walk in-clinic to 400
  Data Source: EMR, Electronic Scheduling
Quality improvement milestones
  Metric: Participate in semiannual face-to-face meetings or seminars organized by the RHP
  Data Source: attendance records, copies of presentations made.

## Slide 9: Description of the Project
DY4 Milestones
Milestone: Increase access to primary care capacity.
  Metric: Documentation of increased number of unique patients.
  Goal: We will increase the number of unique patients who receive a Health Maintenance Exam in the walk in-clinic to 600
  Data Source: EMR, Electronic Scheduling
Quality improvement milestones
  Metric: Participate in semiannual face-to-face meetings or seminars organized by the RHP
  Data Source: attendance records, copies of presentations made.

## Slide 10: Description of the Project
DY5 Milestones
Milestone: Increase access to primary care capacity.
  Metric: Documentation of increased number of unique patients.
  Goal: We will increase the number of unique patients who receive a Health Maintenance Exam in the walk in-clinic to 750
  Data Source: EMR, Electronic Scheduling
Quality improvement milestones
  Metric: Participate in semiannual face-to-face meetings or seminars organized by the RHP
  Data Source: attendance records, copies of presentations made.

## Slide 11: Benefits to the Community
Improvement of utilization rates of preventative, health screening and maintenance exam in a population burdened with significant health care disparities
Reestablish the patient with a Primary Care Provider for subsequent exams
Providing valuable health information to families such as disease prevention and anticipatory guidance
Reduction of vaccine-preventable diseases

## Slide 12: Progress
Milestone Progress:
  Documentation of increased number of patients who participated in the project

## Slide 13: Data
 | DSRIP GROUPING | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Total
DY 2 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | ALL OTHERS | 7 | 10 | 6 | 2 | 5 | 17 | 12 | 19 | 14 | 23 | 37 | 23 | 175
 | MEDICAID | 17 | 9 | 3 | 9 | 20 | 48 | 26 | 46 | 29 | 34 | 108 | 83 | 432
 | UNINSURED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
 | Total Patients | 24 | 19 | 9 | 11 | 26 | 65 | 38 | 65 | 43 | 57 | 145 | 106 | 608
 | % Uninsured | 0% | 0% | 0% | 0% | 4% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
 | % Medicaid | 71% | 47% | 33% | 82% | 77% | 74% | 68% | 71% | 67% | 60% | 74% | 78% | 71%
 | DSRIP GROUPING | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Total
DY 3 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | ALL OTHERS | 24 | 28 | 27 | 48 | 38 | 21 | 26 | 26 | 11 |  |  |  | 249
 | MEDICAID | 106 | 124 | 115 | 134 | 79 | 54 | 91 | 62 | 42 |  |  |  | 807
 | UNINSURED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
 | Total Patients | 130 | 152 | 142 | 182 | 117 | 75 | 117 | 88 | 53 |  |  |  | 1056
 | % Uninsured | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0%
 | % Medicaid | 82% | 82% | 81% | 74% | 68% | 72% | 78% | 70% | 79% |  |  |  | 76%
Unique Patients who received a Well-Child Exam in the Acute Care Clinic
73% Increase
Thus Far

## Slide 14: Innovations
Offered more hours
Tablet Give-Away Incentives
  Health Care Info loaded
  Once a month
Extra staff assigned

## Slide 15: Quality Improvements
Improvements to processes through Value Stream Mapping (VSM) and Rapid Cycle Improvements, PDSA’s

## Slide 16: Next Presentation
Discuss Category-3 outcomes (data)
Description of the process
Milestone Continued Progress
Risk Areas Mitigated
Continuous Quality improvements

## Slide 17
Questions?
Comments?