## Slide 1: Expanding Pediatric Diabetes and Endocrinology Care
Brad Fuhrman, MD
Region 15 RHP Meeting
El Paso First Healthplan, 1145 Westmoreland Drive
July 30, 2014
1:00pm

## Slide 2: Description of the Project
The Department of Pediatrics is the primary provider of Diabetes and Endocrinology care to infants and children in El Paso.
We have, for many years, had a single Endocrinologist to service the entire region.
Appointment wait times range from 6 to 12 months.
Large numbers of children leave the region to find care.

## Slide 3: Description of the Project
The primary goal of this project is to expand the availability of endocrine care by hiring additional pediatric endocrinologists, dieticians, diabetes educators and diabetes nurses to work as a team to improve access to care.

## Slide 4: Description of the Project
DY3 Milestones:
  Implement E-Referral Technology
  Hire 2 FTE Pediatric Endocrinologists
  Bi-Weekly Meetings
  Increase Number of Clinic Visits by 500
  Increase Number of Medicaid and Uninsured Visits by 300

## Slide 5: Description of the Project
DY4 Milestones:
  Bi-Weekly Meetings
  Increase Number of Pediatric Endocrinologists by 0.5 FTE
  Increase Number of Visits over Baseline by 750
  Increase Number of Medicaid and Uninsured Visits Over Baseline by 450

## Slide 6: Description of the Project
DY 5 Milestones:
  Bi-Weekly Meetings
  Increase Number of Visits Over Baseline by 1200
  Increase Number of Medicaid and Uninsured Visits Over Baseline by 720

## Slide 7: Description of the Project
Additional Category 3 Outcomes:
  HbA1c Testing Rate
  Pediatric Quality of Life Assessment

## Slide 8: Benefits to the Community
Greater Access to Pediatric Endocrine Care
Reduced Need to Travel for Pediatric Endocrine Care
Improved Quality of Care
  Fewer Acute Hospitalizations
  Better Quality of Life

## Slide 9: Progress
Bi-Weekly Meetings held to review project status
Three Pediatric Endocrinologists Hired in DY3
DY3 Visit Milestones Nearing Completion
DY3 Medicaid Visits Milestone Nearing Completion
Quality of Life Survey Baseline Established
HbA1c Testing in Pediatric Endocrine Clinic Established

## Slide 10: Data
 | DSRIP GROUPING | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Total
DY2 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | UNINSURED | 1 | 2 | 1 | 5 | 4 | 2 | 4 | 1 | 1 | 2 | 5 | 1 | 29
 | MEDICAID | 55 | 52 | 11 | 32 | 32 | 20 | 54 | 47 | 54 | 28 | 55 | 53 | 493
 | ALL OTHERS | 46 | 39 | 16 | 48 | 53 | 40 | 48 | 47 | 47 | 28 | 61 | 31 | 504
 | Total Encounters | 102 | 93 | 28 | 85 | 89 | 62 | 106 | 95 | 102 | 58 | 121 | 85 | 1026
 | % Uninsured | 1% | 2% | 4% | 6% | 4% | 3% | 4% | 1% | 1% | 3% | 4% | 1% | 3%
 | % Medicaid | 54% | 56% | 39% | 38% | 36% | 32% | 51% | 49% | 53% | 48% | 45% | 62% | 48%
Pediatric Patient Encounters in Endocrinology Clinic -- Baseline
 | DSRIP GROUPING | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Total
DY3 |  |  |  |  |  |  |  |  |  |  | 
 | UNINSURED | 1 | 1 | 2 | 4 | 4 | 1 | 1 | 0 | 0 | 14
 | MEDICAID | 46 | 38 | 37 | 51 | 46 | 47 | 70 | 81 | 92 | 508
 | ALL OTHERS | 54 | 31 | 32 | 60 | 57 | 62 | 86 | 90 | 103 | 575
 | Total Encounters | 101 | 70 | 71 | 115 | 107 | 110 | 157 | 171 | 195 | 1097
 | % Uninsured | 1% | 1% | 3% | 3% | 4% | 1% | 1% | 0% | 0% | 1%
 | % Medicaid | 46% | 54% | 52% | 44% | 43% | 43% | 45% | 47% | 47% | 46%
7% Increase Thus Far

## Slide 11: Innovations
I-Pad administration of Peds QOL Assessment
In-house HBA1c’s

## Slide 12: Quality Improvements
Improvements to clinic processes through Value Stream Mapping and Rapid Cycle Improvements PDSA’s:

## Slide 13
Questions?
Comments?