## Slide 1: EXPANDING NEUROLOGY CARE
Salvador Cruz-Flores MD MPH
Founding Chair, TTUHSC Neurology
Region 15 RHP Meeting
El Paso First Health Plan,
1145 Westmoreland Drive
June 26, 2014 @ 1:00pm

## Slide 2
El Paso population 800,000
About 16 active neurologists
3-6 month waiting time
Large population with epilepsy, cerebrovascular disease, neurodegenerative disorders
El Paso Region Health assessment mentioned the need for neurologists as a priority
GAP ASSESSMENT

## Slide 3: MILESTONES & PROGRESS DY 03
I. To recruit providers (physicians and non physicians)
    2 FTE 2014 (Feb. and July 2014)
    Active pool of applicants for FY 15 to include many specialties
    2ND Interviews completed
  II. To establish an ACGME accredited residency Program in Neurology
      Application will be submitted 8/14
      Target Class: July 2015

## Slide 4: Milestone and Pr0gress DY3
To expand services to include 2 sites, volume of patients seen (outpatient and consults), ambulatory clinic sessions and inpatient consult service(s)
  Outcomes:
    On target for Unique patient count
    2nd site opening prior to 9/14; delay for unique patient count to DY 04
TYPE/YEAR | FY 13 YTD | FY 14 YTD | VARIANCE
Outpatient Visits | 3128 | 3167 | 1.25%
Consults | 281 | 1013 | 260.50%
Diagnostics | 87 | 142 | 63.22%
Procedures | 57 | 99 | 73.68%

## Slide 5: Milestone and Pr0gress DY3
E-Referral
  Implemented a 360° electronic Referrals via Referral Management System.
    Internal referrals within TTUHSC implemented
    External community not incorporated as of yet
Category III DSRIP
  Patient Satisfaction Survey (baseline year)
  Epilepsy: measuring recurrent seizures and hospital readmission (baseline year)
    Enhanced Outpatient Progress Notes completed 2 weeks ago
    Forthcoming data

## Slide 6: Milestone and Pr0gress DY3
VI. 2 Annual Conferences
    May 9, 14: Neurology for Non Neurologists
    June 26, 2014: DSRIP Board Meeting

## Slide 7
Questions?
Comments?