## Slide 1: 1.1 Increasing Access to Ocular Care
Rene Vallejo
Region 15 RHP Meeting
El Paso First Healthplan, 1145 Westmoreland Drive
June 26, 2014
1:00pm

## Slide 2: Description of the Project
Synopsis
Improve utilization rates of clinical preventive services (testing, preventive services, treatment) in target population with identified disparity
Departments Involved:
Texas Tech Surgery- Ophthalmology
Milestones DY3:
4 Hire Ocular Providers currently Recruiting
E Referral-
  Staffing Plan
  Demonstration
  Implement- Internally and externally
Patient Questionnaire – improve by 15%
2 RHP Seminars

## Slide 3: Benefits to the Community
The importance of Diabetic eye exams is a major issues for all Region 15 programs. In the Learning Collaborative it is the most common HEDIS marker not met. In addition, the lack of access to primary care creates more barriers to receiving this screening exam.

## Slide 4: Benefits to the Community Cont.
This Project has increases access to Ocular Care for patients who have
Medicaid and/or uninsured
Putting more resources (Providers) in our clinic.
Reduce time to 3rd appointment from 60 to 8 day
eReferral (RMS) process has streamline referrals within the Texas Tech system.
RMS has also increased communication and follow up between the
primary care provider and the Specialist.
Create a culture of Continuous Quality Improving in the clinic

## Slide 5: Progress
Milestones:
4 Hire Ocular Providers currently Recruiting 75%
E Referral-
  Staffing Plan 100%
  Demonstration and Training 100%
  Implement- Internally and externally 100%
Patient Questionnaire – improve by 15% 75%
2 RHP Seminars 50%
Risk Areas:
  Hiring of Providers prior to deadline- added more resources to recruiting.
Anticipated outcomes:
  Milestones will be met
  New hire May need to be pushed back to DY4

## Slide 6: Innovations
Improvements to processes:
  Educated team on CQI/Rapid Cycle Improvement
  Documented existing process
    Foundation for improvement
    Patient workflow (Lanes)
    Schedule Matrix
    Intake process
    Reduced No-Show rate
    eReferral process improvements

## Slide 7: Improvement Process Cont.
QUALITY Principles
  Your systems are creating your outcomes.
  What you’re doing is getting you what you’re getting
  Must ensure:
    EMPLOYEES do not perform tasks with no value
    PATIENTS do not endure processes of no value
    RESOURCES were used for maximum value
    MAXIMIZE VALUE
    MINIMIZE WASTE

## Slide 8
Questions?
Comments?