## Slide 1: Improving Care and Outcomes of High Risk Newborns after NICU Discharge using the Patient Care Navigation Program
September 28, 2016

## Slide 2: Description of the Project
Patient Care Navigation Program within the High Risk Clinic, a neonatal follow-up program at Texas Tech University Health Sciences Center (TTUHSC) El Paso - Department of Pediatrics
Target infants born at < 32 weeks gestational age and/or infants whose birth weight was < 1500 grams – a cohort of high-risk patients discharged from the El Paso Children’s Hospital (EPCH) – Neonatal Intensive Care Unit (NICU)
Notes: Our solution was to implement a patient navigation program within our existing structure.

## Slide 3
Benefits to the Community
Utilize health care workers, case workers, and other health care professionals as patient navigators.
To provide enhanced social support and culturally competent care to vulnerable high risk patients.
The navigators will help patients navigate the continuum of health care services, assuring timely site-appropriate coordinated services.

## Slide 4: Navigation Services – DY 5 Oct-Aug 2016
 | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Total
Total Services | 151 | 207 | 177 | 135 | 215 | 200 | 291 | 278 | 235 | 107 | 209 |  | 2205
Top 4 services |  |  |  |  |  |  |  |  |  |  |  |  | 
Care Coordination – High Risk Clinic | 61 | 93 | 64 | 62 | 86 | 83 | 112 | 117 | 101 | 43 | 90 |  | 912
Phone calls - Each High Risk Clinic visit | 17 | 34 | 25 | 22 | 22 | 31 | 27 | 44 | 34 | 10 | 17 |  | 283
Care Coordination – other issues | 20 | 25 | 9 | 8 | 22 | 17 | 9 | 9 | 13 | 5 | 16 |  | 153
Education - use of services | 12 | 18 | 22 | 17 | 11 | 9 | 25 | 17 | 18 | 3 | 14 |  | 166
Other services:, Care Coordination – PCP, System navigation – DME issues, Apnea monitoring, care coordination for subspecialty ff-up, barriers to access, insurance services, phone calls – 2 weeks after NICU discharge, prescriptions, social services, home health, referrals to ECI and other rehab facility, triage medical problems, etc. |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 5: Project Milestones and Metrics
Goal: Participate in at least 2 face-to-face meetings /seminars |  | 
DY 3 | 1st meeting: 7/30/2014 | 2nd meeting: 9/24/2014
DY 4 | 1st meeting: 3/25/2015 | 2nd meeting: 6/24/2015
DY5 | 1st meeting: 3/30/2016 | 2nd meeting: 9/28/2016
I-10.2: Increase Number of Unique Patients served by Navigator Program (Number of patients recruited to follow-up at high risk clinic and made it to their first scheduled appointment) | 
DY 3 | Goal: 50 Oct 2013 - Sept 2014: 53 (out of 72 patients recruited = 74%) 57% Medicaid
DY 4 | Goal: 55 Oct 2014 - Sept 2015: 66 (out of 74 patients recruited = 89.1 %) 60.61% Medicaid
DY 5 | Goal: 60 Oct 2015 – Aug 31, 2016 : 57 (out of 74 patients recruited=77%) 64.9% Medicaid (37 of 57)
Notes: Request to change QPI for DY 4 and DY 5 – submitted in August
I-10.2: Increase Number of Unique Patients served by Navigator Program – DY4
Goal: 55 patients (QPI)
I-10.2: Increase Number of Unique Patients served by Navigator Program – DY5
Goal: 60 patients (QPI)

## Slide 6: Category 3 Measures
IT 8.21. Developmental screening in the first 3 years of life.
Indicator: The percentage of children who had screening for risk of developmental, behavioral and social delays using a standardized screening tool documented by 12 months of age. Denominator: Target patients who turn 12 months of age between Jan – Dec of measurement year. Targeted patients: Premature infants enrolled in the program (< 32 weeks and or birth weight < 1500grams). Communication and Symbolic Behavior Scales Developmental Profile (CSBS-DP) – performed during high risk clinic visit on target patients at 9-12 months chronologic age (started in June 2014).
Calendar Year | DY 3 | DY 4 DY5
Total number of patients who turned 12 months of measurement year | (52) | (63) 43
Total number of patients who received developmental screening using CSBS-DP | (13) | (47) 25
Total number of patients who received developmental screening using CSBS-DP (%) | (25%) | (74.6%) 58% Target = 22% August 31, 2016

## Slide 7: Category 3 Measures
Communication and Symbolic Behavior Scales Developmental Profile (CSBS-DP) – performed during high risk clinic visit on target patients at 18-24 months chronologic age. | 
Calendar Year | DY 4 DY5
Total number of patients who turned 24 months of measurement year ( DY4 Born in July –Dec 2013) (DY5 Born between Aug 2014-2016) | 33 38
Total number of patients who received developmental screening using CSBS-DP | 13 18
Total number of patients who received developmental screening using CSBS-DP (%) | 39.4% 47.36% July – Dec 2015 Jan-Aug 2016 13/38 moved 6 had no medicaid,1 expired.

## Slide 8: Category 3 Measures
IT 9.9. Transition record with specified elements received by discharged patients.
Measure: Percentage of patients who received transition record at the time of discharge. Targeted condition – Premature infants < 34 weeks admitted and discharged at El Paso Children’s Hospital – NICU must have documentation of receipt of transition record. Transition record entered as an event by residents/NNPs at discharge (started in June 2014). Tracking done monthly.
October 1– September 30 | DY 3 | DY 4 DY 5* Oct2015-Aug2016
Total patients Discharged < 34 weeks GA | 99 | 99 90
Patients with documented receipt of transition record | 31 | 76 73
Patients with documented receipt of transition record (%) | 31% | 76.7 % 81.11% Goal: 40%

## Slide 9: Category 3 Measures – P4R
IT 8.25. Sudden Infant Death Syndrome Counseling
Measure: Percentage of children 6 months of age who had documented Sudden Infant Death Syndrome (SIDS) counseling. Numerator: Children who had documented SIDS counseling within 4 weeks of birth or by first pediatric visit, whichever comes first. Denominator: Children who turned 6 months of age during the measurement year. Targeted facility. All infants discharged from the El Paso Children’s Hospital – NICU. SIDS counseling incorporated in discharge teaching on all infants discharged from the El Paso Children’s Hospital – NICU. SIDS counseling is entered as an event in Site of Care by residents/NNPs for documentation (tracking started in June 2014).
October 1– September 30 | DY 3 | DY 4 DY 5* Oct2015-Aug2016*
Children discharged from EPCH NICU who turned 6 months of age during the measurement year | 514 | 1035 901
Number of patients who received SIDS counseling | 0 | 737 578
Number of patients who received SIDS counseling (%) | Baseline of 0% None of those patients who received SIDS counseling from June – Sept 2014 had turned 6 months. | 71.2% 64.15%

## Slide 10: P4R Measure attached to IT 8.25.
Tracking of deliveries at UMC with BW <2500g |  |  | 
Year/Month | Number of deliveries BW <2500 g | Total deliveries (live births) at UMC | %
2014 |  |  | 
Total | 271 | 2741 | 10%
2015 |  |  | 
Total (Oct 2014 – Sept 2015) | 240 | 3572 | 6.72%
2016 |  |  | 
Total (Oct 2015 – Aug 2016) | 240 | 3107 | 7.72%

## Slide 11: Quality Improvement (PDSA)
Overall Goals
  Promoting compliance with ff-up appointment at High Risk Clinic Neonatal Follow-up program
  Increase retention of patients enrolled in the program until discharge
  Improve services
  EPCH Pediatric Rehabilitation Therapists now evaluate all patients.
  Now performing Bailey 3 exams through contracted agency until Texas Tech
  Developmentalist hired.
  Increase parent satisfaction

## Slide 12: Quality Improvement (PDSA)
Presented in March 2016
Assess benefits of pediatric physical therapists during Special Care Clinic visits. Promote optimal developmental skills based on patient’s corrected age for milestone.
Enhance awareness to community providers of Special Care Clinic services. Educate on SCC services available to community. Increase referrals and increase current patient population seen.
Bayley 3 Evaluations at the prior to the completion of Special Care clinic visits. The purpose of this evaluation is to follow up outcomes from ongoing outpatient rehabilitative services from hospital discharge to current and identify progress baby has made in 5 developmental areas, towards meeting milestones and preparation for school entrance and parent’s understanding of progress and projection of future needs/services.

## Slide 13: Quality Improvement (PDSA)
Presented in September 2016
PDSA: Assisting with scheduling and or obtaining services outside of SCC appt. After a visit with neonatologist, there is always a couple of patients needing follow up with other subspecialists, renew therapies, rewrite referrals, and obtain DME for patients.
PDSA: Pediatric Rehab therapist during SCC visits. Promote optimal developmental skills based on patient’s corrected age for baby’s milestones. PDSA: Enhance awareness to community providers of SCC services The purpose of this cycle is to: Educate on SCC services available to community. Increase referrals and increase current patient population seen. PDSA: Bayley evaluations – to assess development of infants The purpose of this cycle – follow up outcomes from ongoing outpatient rehab services from hospital discharge to current and identify progress baby has made in 5 developmental areas, towards meeting milestones. PDSA: Frequent visits to hospital emergency room. The purpose of this cycle - follow up outcomes from ongoing hospital emergency rooms vs clinic after hours services or appt to f/u with PCP. Currently seeing increase notification of parents taking baby to emergency room and then being discharged to follow up with PCP.

## Slide 14
Quality Improvement (PDSA)
PDSA: Patients receiving ECI services
The purpose of this cycle – is to determine if in a timely manner our patients receive services
from ECI from date of fax to ECI to start of service?
PDSA: Swift Card Incentive
The purpose of this cycle – is to determine what effect; if any, will rewarding patients parents with an
incentive card ($25) who live outside the city limits and are coming to their first visit have on their
initial appointment scheduled?
PDSA: Welcome Packets Received
The purpose of this cycle – is to determine if there is a change in the number or % of families receiving
Welcome Packets for DY5 compared to DY4?
PDSA: Follow-up phone calls after NICU discharge
The purpose of this cycle – is to determine if having a form of regular communication,
makes us aware of up-coming patient needs or problems?
PDSA: Compliance with 1 yr. Immunizations
The purpose of this cycle – is to determine what percents of patients being seen in HRC between 9-12
months of age are current with their
vaccinations?

## Slide 15: Quality Improvement (PDSA)
13. Mini iPad Give away for keeping the 1st scheduled appointment at High Risk Clinic | 
Patients who made it to their first scheduled appointment are included in the raffle for mini iPad | 
DY 3 show-up rate to first appointment (prior to all QI initiatives including mini iPad raffle): | 53 out of 72 NICU discharges (74%)
DY 4 show-up rate to first appointment after QI initiatives and mini iPad raffles | 66 out of 74 NICU discharges (89.1%)
DY 5 show-up rate to first appointment after QI initiatives and mini iPad raffles | 57 out of 74 NICU discharges (77%)
1st drawing (10/1/14 to 12/15/14 | 12 out of 13 (92.3%)
2nd drawing (12/16/14 to 6/15/15) | 34 out of 38 (89.5%)
3rd drawing (6/17/15 to 12/7/15) | 24 out of 27 (88.8%)
4th drawing (12/08/15 to 5/30/16) | 35 out of 35 (100%)

## Slide 16: Challenges for DY 6
May have difficulty meeting QPI if we have to increase goal (current goal 60) Although not in data, to date we have 64.
For transitional year do not need to increase number.
  Number of patients recruited dependent on EPCH NICU discharges. Always dependent upon admissions.
Possible solutions
  Success depends on our navigators and how efficiently we run the clinic
  Recruitment of Medicaid qualified patients depends on creating a
  Perinatal Center of Excellence and Regionalization of Care.
  Creative projects/incentives to retain patients in the program.

## Slide 17
  Expand the criteria for enrollment in the Patient Navigator Program to include additional NICU graduates who are at risk for adverse outcomes as a consequence of their various diagnoses (e.g. infants with major congenital or chromosomal anomalies) May have application in DY7-10.
  Expand the coverage by enrolling high-risk infants discharged from other NICU facilities in the region referred to Special Care Clinic. May have application in DY7-10.
OTHER SOLUTIONS
Utilize telemedicine conferencing to rural areas and for patients who extended addresses beyond El Paso county.

## Slide 18: Additional Challenges for DY 6
Potential problem with tracking data (those derived from Site of Care) when we change to Cerner documentation. Difficulty securing information and sharing information.

## Slide 19
Questions?
Comments?