## Slide 1: 1.4 Enhancing & Expanding Comprehensive Breast Care Services
Rene Vallejo
Region 15 RHP Meeting
El Paso First Healthplan, 1145 Westmoreland Drive
June 26, 2014
1:00pm

## Slide 2: Description of the Project
Synopsis
Expand and enhance access to specialty care for women with breast disease. Develop a fellowship program, and provide increased access to surgeons with special expertise in breast surgery. Establish a survivor’s program at GBCC, with an emphasis on objective measures of quality of life, and strategies to improve this matric.
Department Involved:
  Department of Surgery- Garbar Breast Care Center (GBCC)
Major Milestones DY3:
Reduce Time-to-3rd Appointment
Survivor Program- 2nd year
Hire Breast Surgeon
Fellowship Program
  Infrastructure to support program
  Application SSO
2 RHP Seminars

## Slide 3: Benefits to the Community
Established in 1994, primary focus was to help the indigent. GBCC treats 1/3 of all breast cancer in El Paso. 4,500 patients seen annually @130 are diagnosed with breast cancer. GBCC has Multi-disciplinary team approach from diagnosis to end of treatment (5 yrs). GBCC is NAPBC- National Accreditation Program for Breast Centers. DSRIP Project will create more access to GBCC services and improving quality of life to those patients. GBCC patients are 45% Medicaid or uninsured

## Slide 4: Progress
Milestones:
Reduce Time-to-3rd Appointment 50%
Survivor Program- 2nd year 80%
  SF36 Quality of Life Survey
  Dietitian Services
  Psychiatry/Counseling Services
Hire Breast Surgeon 40%
Fellowship Program
  Infrastructure to support program 100%
  Application to SSO 95%
2 RHP Seminars 50%
Risk Areas:
  Hire Breast Surgeon- Hired Search firm
Anticipated outcomes:
  MUST Hire DY3
  Meet all other milestones
Connection:
  Working with Texas Tech Internal Medicine Oncology Department

## Slide 5: Innovations
Improvements to processes:
  Educated team on CQI/Rapid Cycle Improvement
  Survivor Program- Patient flow
  Developing Fellowship
  SF36 / EMR

## Slide 6
Questions?
Comments?