## Slide 1: Improving Care and Outcomes of High Risk Newborns after NICU Discharge using the Patient Care Navigation Program
Ma Teresa C Ambat, MD
Region 15 RHP Meeting
El Paso First Healthplan, 1145 Westmoreland Drive
March 25, 2014
1:00pm

## Slide 2: Description of the Project
Patient Care Navigation Program within the High Risk Clinic, a neonatal follow-up program at Texas Tech University Health Sciences Center (TTUHSC) El Paso - Department of Pediatrics
Target infants born at < 32 weeks gestational age and/or infants whose birth weight was < 1500 grams – a cohort of high-risk patients discharged from the El Paso Children’s Hospital (EPCH) – Neonatal Intensive Care Unit (NICU)
Notes: Our solution was to implement a patient navigation program within our existing structure.

## Slide 3: Project Milestones and Metrics
P2.1: Number of People Trained as Patient Navigators
Goal: 1 Additional Patient Navigator hired and trained
DY 3: Met milestone, 1 person hired – start date 8/20/2014
DY 4 & 5: Excluded from milestones
P2.2: Develop Outreach Plan to enroll patients in Navigation Program
Goal: Complete Patient Outreach Plan
DY 3: Completed and submitted 8/7/14
DY 4 & 5: Excluded from milestones

## Slide 4: Project Milestones and Metrics
P-10.1: (Customized) Report on types of services provided to high risk patients enrolled in the program
Goal: Complete report on those services provided to High Risk Patients
DY 3
Navigators use EMR form to document the services (started in 6/2014).
Total services from June – Sept 2014: 326
Top 5 services: Care Coordination – High Risk Clinic, Care Coordination – PCP, System navigation – DME issues, Apnea monitoring, Phone calls – prior to High Risk clinic visit
Notes: IT support uses an identifier to track this form to generate the report.

## Slide 5: Navigation Services – DY 4
 | Oct | Nov | Dec | Jan | Feb | Mar | Total
Total Services | 292 | 160 | 202 | 230 | 288 | 85 | 1257
Top 5 services |  |  |  |  |  |  | 
Care Coordination – High Risk Clinic | 80 | 51 | 77 | 73 | 99 | 27 | 407
Phone calls - Each High Risk Clinic visit | 44 | 20 | 17 | 25 | 38 | 10 | 154
Education - appropriate use of services | 14 | 6 | 16 | 8 | 21 | 9 | 74
Care Coordination - PCP | 25 | 9 | 16 | 8 | 14 | 1 | 72
Care Coordination -other issues | 7 | 3 | 4 | 14 | 23 | 6 | 57
Other services: Care Coordination – PCP, System navigation – DME issues, Apnea monitoring, care coordination for subspecialty ff-up, barriers to access, insurance services, phone calls – 2 weeks after NICU discharge, prescriptions, social services, home health, referrals to ECI and other rehab facility, triage medical problems, etc. |  |  |  |  |  |  | 

## Slide 6: Project Milestones and Metrics
P-8.1: Participate in semi‐annual face-to-face meetings or seminars organized by the RHP |  | 
Goal: Participate in at least 2 face-to-face meetings/seminars |  | 
DY 3 | 1st meeting: 7/30/2014 | 2nd meeting: 9/24/2014
DY 4 | 1st meeting: 3/25/2015 | 2nd meeting: TBD
I-10.2: Increase Number of Unique Patients served by Navigator Program | 
DY 3 | Goal: 30  50 Patient enrolled Oct 2013 - Sept 2014: 54 (out of 74 patients recruited = 73%)
DY 4 | Goal: 55 Patient enrolled Oct 2014 – March 23, 2015: 32 (out of 38 patients recruited = 84 %)
Notes: Request to change QPI for DY 4 and DY 5 – submitted in August
I-10.2: Increase Number of Unique Patients served by Navigator Program – DY4
Goal: 55 patients (QPI)
I-10.2: Increase Number of Unique Patients served by Navigator Program – DY5
Goal: 60 patients (QPI)

## Slide 7: Category 3 Measures
IT 8.21. Developmental screening in the first 3 years of life.
Indicator: The percentage of children who had screening for risk of developmental, behavioral and social delays using a standardized screening tool documented by 12 months of age. Denominator: Target patients who turn 12 months of age between Jan – Dec of measurement year. Targeted patients: Premature infants enrolled in the program (< 32 weeks and or birth weight < 1500grams). Communication and Symbolic Behavior Scales Developmental Profile (CSBS-DP) – performed during high risk clinic visit on target patients starting at 9 months chronologic age (started in June 2014).
 | DY 3 | DY 4
Total number of targeted patients who turned 12 months of measurement year | 13 | 17
Total number of targeted patients who received developmental screening using CSBS-DP | 52 | 57
Total number of targeted patients who received developmental screening using CSBS-DP (%) | 25% | Goal 26.25% As of Feb 2015: 30%

## Slide 8: Category 3 Measures
IT 9.9. Transition record with specified elements received by discharged patients.
Measure: Percentage of patients who received transition record at the time of discharge. Targeted condition – Premature infants < 34 weeks admitted and discharged at El Paso Children’s Hospital – NICU must have documentation of receipt of transition record. Transition record entered as an event by residents/NNPs at discharge (started in June 2014). Tracking done monthly.
 | DY 3 | DY 4
Total patients Discharged < 34 weeks GA | 99 | 32
Patients with documented receipt of transition record | 31 | 26
Patients with documented receipt of transition record (%) | 31.3% | Goal: 32.8% As of Feb 2015: 81%

## Slide 9: Category 3 Measures
IT 8.25. Sudden Infant Death Syndrome Counseling
Measure: Percentage of children 6 months of age who had documented Sudden Infant Death Syndrome (SIDS) counseling. Numerator: Children who had documented SIDS counseling within 4 weeks of birth or by first pediatric visit, whichever comes first. Denominator: Children who turned 6 months of age during the measurement year. Targeted facility. All infants discharged from the El Paso Children’s Hospital – NICU. SIDS counseling incorporated in discharge teaching on all infants discharged from the El Paso Children’s Hospital – NICU. SIDS counseling is entered as an event in Site of Care by residents/NNPs for documentation (tracking started in June).
 | DY 3 | DY 4
Children discharged from EPCH NICU who turned 6 months of age during the measurement year | 514 | 918
Number of patients who received SIDS counseling | 0 | 664
Number of patients who received SIDS counseling (%) | Baseline of 0% None of those patients who received SIDS counseling from June – Sept 2014 had turned 6 months. | Goal: 5% As of Feb 2015: 72%

## Slide 10: P4R Measure attached to IT 8.25.
Tracking of deliveries at UMC with BW <2500g |  |  | 
Year/Month | Number of deliveries BW <2500 g | Total deliveries (live births) at UMC | %
2014 |  |  | 
October | 10 | 338 | 
November | 4 | 296 | 
December | 21 | 332 | 
2015 |  |  | 
January | 18 | 309 | 
February | 5 | 260 | 
Total as of Feb 2015 | 58 | 1535 | 3.8%

## Slide 11: Quality Improvement (PDSA)
Goals
  Promoting compliance with ff-up appointment at High Risk Clinic Neonatal Follow-up program
  Increase retention of patients enrolled in the program until discharge
  Improve services
  Increase parent satisfaction

## Slide 12: Quality Improvement (PDSA)
1. Phone call reminders to parents of SCC appointment
Changed the day and time of phone call reminder to parent (Wednesday PM, Thursday AM) Early notification allowed for early identification of problems/barriers to keeping appointment and address problems in time which allowed parents to make any arrangements needed (examples: transportation arrangement for appointment, child care arrangements for siblings)
2. Family meetings prior to hospital discharge
First meeting scheduled 1 week prior to discharge, ff-up meeting 1-2 days prior to discharge
3. Hospital discharge welcome packet to SCC services
Parents are provided welcome packet prior to hospital discharge which contains information on Texas Tech pediatric services, phone numbers of the High Risk Clinic, community agencies, growth and development baby booklet
Strategies 2 and 3 allowed for better understanding of High Risk Clinic services, established rapport between families and clinic and reinforced the role of navigators/coordinators as advocate and liaison to assist families in successful transition from NICU to home

## Slide 13: Quality Improvement (PDSA)
4. Texas Tech Welcome to first High Risk Clinic Visit
On the first High Risk Clinic visit, navigators review with families information on clinic visit processes and care navigation services
Reiterated importance of high risk clinic visits and its impact on long-term outcomes to encourage compliance and parents’ participation in the care of their infants Provided continued reassurance to families that they have partners who can help them be successful in taking care of their babies
5. Follow up appointment scheduled prior to leaving exam room
Reduced time in the clinic and promote satisfaction Prevented missed appointment by having the follow-up appointment scheduled prior to leaving the exam room
6. Scheduling High Risk Clinic visits at 1 hour intervals
Reduced waiting time, cancellation and rescheduling of appointment Reduced pressure placed on practitioner to readily see patient Spacing all SCC visits to 1 hour intervals allowed practitioner to have longer face-to-face encounter with patients

## Slide 14: Upcoming Projects
Preemie Baby’s Day Out – May 7, 2015, 2-5PM at Texas Tech
  Provide opportunities for gathering of families to connect with one another for support as they share their stories and a time to honor them
  Educational presentations on developmental care and interventions, appropriate use of services and community resources to assist families as they increase their ability and confidence to care for their infants after NICU discharge

## Slide 15
Questions?
Comments?